Survey of marine turtle use by communities and turtle nesting habitat monitoring in Fiji – Interim Progress Report

PART 1: GENERAL NARRATIVE REPORT

| Project/ Programme Name: | PEUMP Programme By-catch and Integrated Ecosystem Management Initiative: Survey of marine turtle use by communities and turtle nesting habitat monitoring in Fiji |
| --- | --- |
| Project/Programme Number(s): | FJ205900 |
| Web Link(s) to project/programme strategic plan or other useful documents: |  |
| Reporting Period: | Interim Progress Report - 3 month Report |
| Project/Programme Start Date (FY): | 15th November 2020 |
| Report Completed by: | Duncan Williams |
| Date Report Completed (MM/YR): | 03/21 |

Reflections on Success and Failure

1)    Key Outcomes and Impacts Achieved

This is the first interim progress report and covers the period from project signing 15th November 2020 up to 28th February 2021. SPREP is leading the By-catch and Integrated Ecosystem Management (BIEM) Initiative, which is Key Result Area 5 of the Pacific European Union Marine Partnership (PEUMP) Programme. Key Result Area 5.4 is focused on assessing the extinction risk of endangered marine species. WWF- Pacific has been contracted to implement the PEUMP Programme BIEM Initiative: Survey of marine turtle use by communities and turtle nesting habitat monitoring in Fiji specific project activities in Fiji project which contributes toward KRA 5.4.

The project’s overall goal is to better understand Fiji’s coastal community motivations for marine turtle use and trade, patterns of direct and indirect take of different turtle species in Fiji and record environmental parameters at specified index beaches in Fiji in order to inform the assessment of regional extinction risk and policy aimed at reducing the exploitation of marine turtles.

Although there has been progress in delivering project activities, the project has been affected by tropical cyclone Yasa and TC Ana. A report on the impact of TC Yasa, an internal WWF report on the impact of TC Ana to Vanua Levu and a tropical cyclone outlook for the 2020/2021 period issued by the Fiji Meteorological service (https://www.met.gov.fj/index.php?page=tcoutlook) are attached for reference.

Despite the setbacks, activities have been initiated however there have been delays as a result of the cyclones.  Progress to date as measured against specific milestones is detailed below.

| Milestone | Progress | Deliverables / Indicators | Due date |
| --- | --- | --- | --- |
| Collect temperature and other environmental data necessary to inform potential impacts of the climate on turtle reproduction patterns | Fifteen (15) data loggers and one (1) weather station have been received by WWF Pacific from SPREP in December and WWF Australia in January respectively. The data loggers and weather stations were to be setup on Kavewa in February however field deployment was hampered by tropical cyclone Ana. The data loggers and weather stations will now be deployed in March/April at the same site. | Data generated and submitted to ‘Cool Turtle’ database. | 31/05/21 |
| Identify and agree survey sites based on recent perception surveys, turtle stakeholder consultation reports, expert feedback and other relevant literature. | Completed. Priority survey sites had been proposed following the divisional consultations leading up to the Fiji sea turtle steering committee meeting in 2019. These were finalised following consultations between WWF and the Ministry of Fisheries and project partners (Mamanuca Environment Society (MES) Conservation International (CI),the Institute of Applied Sciences of USP (USP IAS) and official community representatives and DnVs from Macuata and Bua)) prior to and at commencement of this project. A map detailing the survey sites is provided as Appendix 1. | Survey site selection report submitted to Government Ministries, SPREP and partners. | 30/11/20 |
| Consultations with partner(s) to seek endorsements from the relevant provincial administrations to secure relevant authorisations and develop a plan for implementing the survey methodology for estimating turtle harvest rates (this includes identifying suitable men and women community monitors and supporting their attendance at the workshop) | Consultations with the Ministry of Fisheries (MoF), Mamanuca Environment Society (MES) Conservation International (CI),the Institute of Applied Sciences of USP (USP IAS) and official community representatives and DnVs from Macuata and Bua) had been conducted prior to project signing with verbal and/or email approval to conduct surveys in all respective sites provided. The project team has since been in contact with relevant partners and community focal points following the departure of Tropical cyclones Yasa and Ana to determine the severity of impacts and feasibility of conducting fieldwork/surveys in all sites. Approvals for entering community sites to undertake the surveys have been provided by official community representatives and implementing partners. In addition, officers from the relevant provincial offices (Serua, Macuata, Ba and Bua) will accompany the survey teams into the field when the project teams conduct the community monitoring training workshops. A consolidated Report Back to Office report is provided as Appendix 2. | Consultation meetings conducted and meeting reports submitted to Government Ministries, SPREP and partners. | 31/12/20 |
| Organise community monitoring training workshop in selected regions in Fiji (Northern, central, southern and western divisions) | There has been progress toward achieving this milestone despite the adverse effects of the cyclones. Fifteen (15) volunteers were selected in January to assist the project team and will assume the role of sea turtle conservation monitors. The volunteer monitors comprise of nine (9) female and five (5) males. All the volunteers are undergraduate students with backgrounds in fisheries, marine management and/or environmental studies. A flyer was circulated to MoF and USP with twenty three (23) applications received. A two-day sea turtle monitor awareness training workshop was held on the 25th and 26th of February at the Southern Cross Hotel in Suva and organised with support from SPREP. The objectives of the workshop were to familiarise the sea turtle conservation monitors with National efforts to conserve sea turtles; Community based sea turtle management; Ongoing sea turtle Research; and to socialise the Sea turtle nesting and snapshot and use survey forms. The media release from the training workshop in Suva can be found at: https://www.wwfpacific.org/?uNewsID=36639 The volunteer monitors will carry out the community snapshot survey, turtle nesting surveys and provide support with the community monitoring training workshops. The community training workshops will now take place by mid-March. | 10 x workshop reports with signed attendance sheets and photographic evidence submitted to Government Ministries, SPREP and partners | 31/12/20 |
| Oversee and support community monitors during data collection phase | This will take place after the deployment of the volunteer sea turtle conservation monitors and community training workshops in mid-March. |  | 31/05/21 |
| Undertake the surveys (community snapshot and turtle interaction) and deliver community consultation workshops to review and share findings | This will take place after the deployment of the volunteer sea turtle conservation monitors and community training workshops in mid-March. | Completed survey forms collated | 31/05/21 |
| Develop communications plan | A draft communications plan has been submitted for approval and is attached as appendix 3 | Communications plan agreed with Government Ministries, SPREP and partners. | 31/12/20 |
| Develop communications products (e.g. Press and social media releases, interviews, reports) in line with PEUMP Programme Communications and Visibility Strategy | A draft communications plan has been submitted for approval which outlines communications products that will be delivered beginning with the deployment of the volunteer sea turtle conservation monitors and community training workshops in mid-March. | Communication products signed off by SPREP and EU. | 31/1/21 |

Effective Implementation of Workplans and Budgets

Although there has been progress in delivering certain project activities as noted above, the impact of severe tropical cyclone Yasa mid-December 2020 and TC Ana in February 2021 has delayed start-up and overall project activity implementation and this is reflected in the slow burn rate as reflected in the financial reports. Despite the setbacks, activities have been initiated/resumed as noted by the recent selection and training of volunteer monitors with field deployment and training of community monitors and implementation of surveys to be well underway by the middle of March and which will see an increase in burn rates for the next reporting period.